## Instructions
Using the Status tracker / - At the end of each week, update the status of all activities completed during the week. / - The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week). / - Fill in hours spent on each activity during the current week. / - If 5 team members each spent an hour, that counts as 5 hours. / - Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks. / - During the planning phases, identify the activities to be done during each week. / - If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front). / - For new activities, identify the type of activity - documentation, coordination, estimation etc. / - At the end of each week, plan ahead for the following week Identify people responsible for each activity. / - Estimate the hours needed for the activity / - Error in estimation is calculated using a formula that’s already applied.

PROJECT NUMBER	12
PROJECT NAME	IOT Dashboard and Analytics using superset
PROJECT MENTOR (sponsor)	Santosh B
TEAM MEMBERS	R.S.Subbulakshmi
	Arnav Kapoor
	Debojit Das
	Chinni Venkata Charan
	Ujwal Narayan N

## Status
PROJECT NUMBER	12
PROJECT NAME	IOT Dashboard and Analytics using superset
PROJECT MENTOR (sponsor)	Santosh B

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 1 (August 6- August 12)
Fix meeting with client	Coordination	Ujwal Narayan N	0.5	0.3	Done		0.2	66.6666666667
GIT Repository setup	Preparation	R.S.Subbulakshmi	1	1.5	Done		-0.5	33.3333333333
Client meeting	Coordination	Ujwal Narayan N	4	3	Done		1	33.3333333333
Learning Superset	Preparation	Arnav Kapoor,Chinni Venkata Charan	3	4.5	Done		-1.5	33.3333333333
Week 2 (August 13 - August 19)
Learning Superset	Preparation	Debojit Das,R.S.Subbulakshmi,Ujwal Narayan N,	4	4	Planned		0	0
Gitlab Structure Setup	Preparation	R.S.Subbulakshmi	0.25	0.25	Done		0	0
Team Meeting	Coordination	Ujwal Narayan N	1	1	Done		0	0
Status tracker update	Documentation	Chinni Venkata Charan	0.25	0.25	Done		0	0
Client meeting	Coordination	Arnav Kapoor	1.5	1.5	Done		0	0
Week 3 (August 20 - August 26)
Learning Superset	Preparation	Arnav Kapoor,R.S.Subbulakshmi	3	2.5	Done		0.5	20
Status tracker update,minutes of meeting	Documentation	Chinni Venkata Charan	0.5	0.5	Done		0	0
Project Concept Doc	Documentation	Debojit Das	0.5	0.5	Done		0	0
Client meeting	Coordination	Ujwal Narayan N	1	1.5	Done		-0.5	33.3333333333
Week 4 (August 27 -September 2)
Status tracker update	Documentation	Chinni Venkata Charan	1.5	2	Delayed	Mid Sems	-0.5	25
Learning Superset	Preparation	R.S.Subbulakshmi,Arnav Kapoor,Chinni Venkata Charan	4	3.5	Done	Mid Sems	0.5	14.2857142857
SRS Draft,minutes of meeting	Documentation	Ujwal Narayan N	1.5	1.5	Done		0	0
Fix meeting with client,Learning Superset	Coordination	Debojit Das	0.25	0.25	Done
Week 5 ( September 10 – September 16)
Creating Example Dashboards	Development	Debojit Das,R.S.Subbulakshmi,Chinni Venkata Charan	4	4	Done	Got an overview on how to create dashboards	0	0
Team Meeting	Coordination	Debojit Das	0.5	0.5	Done		0	0
Status tracker update	Documentation	Chinni Venkata Charan	0.5	0.5	Done		0	0
Login and signup	Development	Arnav Kapoor,Ujwal Narayan N	4	4	Ongoing		0	0
Week 6 (September 17 – September 23)
Quering different kind of databases	Development	R.S.Subbulakshmi,Chinni Venkata Charan	4	3	Done	Assignments	1	33.3333333333
Project Plan Docx,statustracker update	Documentation	Chinni Venkata Charan	2.5	2.5	Done		0	0
Team Meeting	Coordination	R.S.Subbulakshmi	1	0.5	Done		0.5	100
Client meeting,Creating Charts	Coordination	Debojit Das	1	1	Done
Login and signup	Development	Ujwal Narayan N,Arnav Kapoor	4	4	Ongoing		0	0
Week 7 (September 24 -September 30)
Visualizing databases	Development	Chinni Venkata Charan	1	1	Done		0	0
Project Plan Docx,statustracker update	Documentation	Chinni Venkata Charan,R.S.Subbulakshmi	1	1	Done		0	0
Team Meeting	Coordination	R.S.Subbulakshmi	1	1	Done		0	0
Created roles and user	Development	R.S.Subbulakshmi	2	2	Done		0	0
Single login	Development	Ujwal Narayan N	1	1	Ongoing		0	0
Week 8 (October 1 – October 7)
Project Plan Docx,statustracker update	Documentation	Debojit Das,R.S.Subbulakshmi,Chinni Venkata Charan	1	1	Done		0	0
Created ppt and demo video	Documentation	Debojit Das,R.S.Subbulakshmi,Chinni Venkata Charan,Arnav Kapoor ,Ujwal Narayan	2		Ongoing
Team Meeting	Coordination	R.S.Subbulakshmi	2	3	Done		-1	33.3333333333
Created seperate permissions for different roles	Development	R.S.Subbulakshmi	2	4	Ongoing		-2	50
Single login	Development	Ujwal Narayan N	1	1	Ongoing		0	0