## TestPlan
Test Planner and Tracker			12	Debojit Das, Ujwal Narayan, Subbulakshmi, Arnav Kapoor, Venkata Charan Chinni
Test / No. ID	Related / Use case	Pre-conditions	Test Description (steps)	Expected Outcome	R1 Outcome (color code / cell background)	Possible reasons for failure	Comments
1	Register using googlel (Other Oauth Providers)	None	1.Users enter the email-id 2. Enter username 3. Enter password 4. Confirm password 5.Submit on the Oauth providers page	Registered Successfully/ ID already in use	Success	Error in creating user
2	Single sign-on/login	Register	1.User enters username 2. Enter password If already registered and correct details - successful login else - unsuccessful	Login Successful/Invalid username or password	Success	Login failed
3	Conversion of ODS to ADS	None	Take the ODS (Operational Data Store) and use 3rd party applications/parser to get ADS	Everything should be in ADS	Ongoing	Error in conversion	Havent got the access to databases
4	Choosing of Templates	Conversion of ODS to ADS	1.Enter application 2.Choose template 3.Visualize for chosen database and table 4.View changes in graphs for given inputs in the filter boxes	4 working templates	Ongoing	Template wrongly created	Created sample queries for dummy databases (mySQL,sqlite3)
5	Displaying and Viewing Data	Login, Choosing of Templates	Improve upon the dashboard. Also integrate templates into the application	A complete functional app with good GUI	Success	Not to be presented for R1
6	Contribution to Superset	Displaying and Viewing Data	Contribute the code back to Superset	Successfully contributed	Delayed	Not to be presented for R1	Pending reviews
7	Loging as a user with specific roles	User already created , designated roles	1.Login as specific user 2.Dashboard changed according to the user’s roles and permissions 3.Can only view datasources for which permission given 4.Can view,update,delete and query databases for which the user has permissions	When attempting to access unauthorized databases , error statement telling that the user does not have neccessary permissions will be displayed .All data sources for which the user has permissions will alone be displayed to be accessed	Success	Roles not properly created .Users not properly designated with roles
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30

## Instructions
Test plan Instructions

It is particularly important that you create a substantial set of Acceptance
Tests. These are tests based on the requirements document. Each acceptance
test should describe an operation to be performed by the user, and the
expected outcomes from that operation. The objective is to define a
comprehensive set of tests that between them cover all the features in the
requirements document. The tests should preferably cover all the frequent
"normal use" scenarios, as well as commonly occurring exception scenarios.
Each acceptance test must be described as a set of user instructions for
performing the test, much like a user manual. The outcomes description
specifies how the user knows whether the test succeeded or failed. The
reason for defining acceptance tests early in the life-cycle is to
facilitate "test-driven development". Developers can look at the acceptance
tests that their module must satisfy, and thereby know exactly what behavior
is expected from their module. Make sure to update these if/when
requirements change. Make sure to follow the suggested format.

## Monopoly Example
Monopoly Test Planner and Tracker (example)
	Game in test mode implies that the tester can control the outcome of the dice roll - assume dice roll can exceed 12 for testing.
	Note that some of the test cases require previous test cases to be completed as a precondition.
Acceptance tests

Test No.	User Story covered	Preconditions	Test Description	Expected Outcome	R1 Outcome	R2 Outcome
1	Move Player	Game is in test mode. / Game is in initial state. / Number of Players: 1 / Player 1 Name: Tester1	Player 1 Dice Roll Total : 5 / Player 1 End Turn	Player 1 is located at Reading Railroad cell.
2	Move Player	Test 1 completed	Player 1 Dice Roll Total : 5 / Player 1 End Turn	Player 1 is located on Jail cell.
3	Move Players in Turns	Game is in test mode. / Game is in initial state. / Number of Players: 2 / Player 1 Name: Tester1 / Player 2 Name: Tester2	Player 1 Dice Roll: 5 / Player 1 End Turn	Player 1 is located at Reading Railroad
			Player 2 Dice Roll: 3 / Player 2 End Turn	Player 2 is located at Baltic Avenue
4	Pass Go	Game is in test mode. / Game is in initial state. / Number of Players: 1 / Player 1 Name: Tester 1	Player 1 Dice Roll: 39 / Player 1 End Turn	Player 1 is located at Boardwalk
			Verify Player 1 bank balance	Player 1 has $1500
5	Pass Go	Game is in test mode / Game is in initial state. / Number of Players: 1 / Player 1 Name: Tester 1	Player 1 Dice Roll: 40 / Player 1 End Turn	Player 1 is located on GO cell
			Verify Player 1 bank balance	Player 1 has $1700	Go money paid out only after passing GO, not when it is reached.
6	Pass Go	Game is in test mode. / Game is in initial state. / Number of Players: 1 / Player 1 Name: Tester 1	Player 1 Dice Roll: 41 / Player 1 End Turn	Player 1 is located at / Mediterranean Avenue
			Verify Player 1 bank balance	Player 1 has $1700